PMP EXAM PREPARATION

EARNED VALUE PERFORMANCE MEASUREMENT

Additional Sample Questions

Answers and Explanations

Walter Wawruck

September 11, 1998

Scenario #1

Work Package	Budget	ACWP	BCWP

Survey	500	2,000	400

Remove Debris	2,000	3,500	2,000

Dig Hole	3,000	2,000	2,800

Place Forms	1,200	1,000	1,100

Pour Concrete		5,000		3,000		2,500

Project Total	11,700	11,500	8,800

1.	Assuming that the Cost Performance Index, as demonstrated up to the reporting date, remains constant to the completion of the project, what is the EAC for the project?

CPI to date	=	BCWP	=	 8,800		(1)

ACWP		11,500

CPI at completion   =   Budget   =   11,700	(2)

EAC           EAC

So, if (1) = (2), EAC = 11,700 x 11,500

8,800

EAC = 15,290

2.	Assuming that after the reporting date, the remaining portions of deliverable results from each work package can be provided for the cost that was originally budgeted for those portions, what is the EAC for the project?

Total project budget			11,700

Loss:	Budget for physical results to date = BCWP =		8,800

Leaves:		Budget for physical results which remain

to be completed = BCWR =		2,900

(R stands for “Remaining”)

Assuming then that ACWR = BCWR;

EAC	=	ACWP + ACWR

=	11,500 + 2,900

=	14,400

3.	Which activity(es) has(have) the least favourable cost variance to date?

CV = BCWP - ACWP

CV is the least for “Survey”

CV	=	400 - 2,000

=	- 1,600

4.	What is the projected schedule variance for the total project when every work package is completed?

Trick question.  By definition, at the completion of the project, BCWP = BCWS = Budget for every work package, and for the entire project.  In other words, all the value available to be earned, has been earned.  So:

SV = BCWP - BCWS = 0, by definition.

Scenario #2

Item	BCWS	ACWP	BCWP

1	10,000	11,000	10,000

2	9,000	8,000	7,000

3	8,000	8,000	8,000

4	7,000	12,000	5,000

5	6,000	12,000	6,000

Assume that all figures are project-to-date, that all items were scheduled to be completed by now, and that performance on all is credited in $1,000 units.

5.	Of the items which have been completed, which was farthest over budget?

Items 1, 3, and 5 are completed, since BCWP = BCWS.  Of these, the cost variance is least favourable for Item 5.  See below:

Item	BCWP - ACWP = CV

1	10,000 - 11,000 =  - 1,000

3	  8,000 -   8,000 =       0

5	  6,000 - 12,000 =  - 6,000

6.	Which item appears likely to have the largest cost over-run?

Item 4, is not yet completed, and already has the greatest negative cost variance:

CV to date	=	BCWP - ACWP

=	5,000 - 12,000

=	- 7,000

7.	Of the items not yet completed, which one has fallen farthest behind in the value of physical output as measured by schedule variance?

Items 2 and 4 are not completed.  See explanation for No. 5 above.  For these two:

Item	BCWP - BCWS = SV

2	7,000 - 9,000 = - 2,000

4	5,000 - 7,000 = - 2,000

Items 2 and 4 have fallen equally far behind in the value of physical output.

8.	Of the items not yet completed, which one has fallen farthest behind in the proportion of physical output as measured by the Schedule Performance Index?

Using the information from the explanation for No. 7 above, the SPI is a measure of proportionate or relative physical progress:

Item	BCWP/BCWS = SPI

2	7,000/9,000 = 0.78

4	5,000/7,000 = 0.71

Item 4 is farther behind in proportion of planned output.

9.	For which item is there the greatest spending variance to date?

Tricky question.  A positive variance means an item is underspent.  In this case,

BCWS - ACWP is greatest for item 2:

9,000 - 8,000 =  + 1,000 = Spending Variance.

Scenario #3

Item	BCWS	ACWP	BCWP

1	10,000	10,000	10,000

2	10,000	8,000	10,000

3	10,000	8,000	8,000

4	9,000	12,000	10,000

5	10,000	12,000	12,000

6	10,000	10,000	12,000

7	12,000	12,000	10,000

8	10,000	8,000	9,000

9	12,000	10,000	11,000

10.	For which item(s) is the physical progress in producing the deliverable results ahead of that planned up to the reporting date?

Physical progress ahead of plan is indicated either by a Schedule Variance that is positive, or a Schedule Performance Index greater than 1.0.  By inspection:

Item	BCWP - BCWS = SV

4	10,000	- 9,000	=	+ 1,000

5	12,000	- 10,000	=	+ 2,000

6	12,000	- 10,000	=	+ 2,000

For all other items, SV( 0

11.	Among the items with an SPI = 1.0, which one has the greatest CPI to date?

SPI = BCWP/BCWS

SPI = 1.0 only for Items 1 and 2.

Item	BCWP/ACWP = CPI

1	10,000/10,000 = 1.0

2	10,000/8,000   = 1.25

CPI is greater for Item 2.

12.	Which two items have the least favourable CPI to date?

Items 4 and 7 have the smallest or least favourable CPIs.  In each case,

CPI	=	BCWP/ACWP

=	10,000/12,000

=	0.83

13.	If all nine items are taken together, is the project underspent or overspent to date?

Planned “Spending” to date is 	the sum of all BCWS’s  =	93,000

Actual “Spending” to date is the sum of all ACWP’s   =		90,000

Hence, project is underspent by		3,000

The spending variance is positive.

14.	Which of the items can be said with certainty, to be fully completed?

There is insufficient information to determine if any of the items are fully completed.  Hence, the answer must be NONE of the items.

15.	How would your client react if you informed him or her that you are $2,000 behind schedule on Item 3.

This will not be an exam question.

I don’t know about your clients, but mine would likely give me strange looks if I reported schedule variance in monetary units.

The earned value measurements do not give practical, or accurate indications of schedule status.  For this purpose, techniques like logic networks and CPM analysis can be employed to display both historical and forecast schedule performance in time units - days early or days late, for instance.